## Sheet1
Module | Material | FG Referance # | Customer Style | Color Description | Subcon Type | Description | Fabric Design | Order Reason | Special Services | CPO | Region / (Country) | Name | Season | External Material Group | Customer | Customer Dept | Sales Order | Item | Prod.order | SO qty. | Order qty. | SMV | Effi. | Emp | Pcs/day | #days | Cut date | Start date | Finish date | Expected prod.end date | Deliv.date | Del.status | Cut qty. | In qty. | Out qty | Fab In H date | Acc In H date | QCO | Product Category Name | Gender | Relative Similarity | Remarks | L.Curve | Planning Fab | Planning Acc | Approval DD | Section
H403 | 7000796029 | F536690BLAF5001 | 536690 | BLACK | B/CO | WR CR HINK TNKI SHELF SLD BLA REG CORE | SD | Bulk |  | 124434 | United States | THARANGAGAMAGE | 3SU | Lands'End | 100262 | LE CORE - WOMENS SWIM | 1000869667 | 10 | 8002641801 | 341 | 341 | 6.63 | 22.5 | 16 | 248 | 1.3736 | 2023-01-12 | 2023-01-18 | 2023-01-20 | 2023-01-31 | 2023-02-06 | 6 | 341 | 0 | 0 | 2022-10-26 | 2022-11-22 | QCO | Swimsuit | WOMEN | 0% |  | SOQ1[Day-1] |  |  |  | SECTION 4
H403 | 7000836197 | FUW0UW046250G2 | UW0UW04625 | VINTAGE TROPIC BLUE | IHS/SPG | SF23 UW0UW04625 1PC PRTVTG TRP BLUE EU |  | Bulk |  | SUPF23 TH UW0UW046250G2 TOP | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 2000179747 | 10 | 8002695360 | 5 | 5 | 13.21 | 5 | 25 | 51 | 0.0979 | 2023-01-17 | 2023-01-20 | 2023-01-20 | 2023-02-02 | 2023-02-09 | 8 | 0 | 0 | 0 |  | 2023-02-09 |  | Swimsuit | WOMEN | 0% |  | INITIAL CURVE[Day-1] |  |  |  | SECTION 4
H403 | 7000836197 | FUW0UW046250G2 | UW0UW04625 | VINTAGE TROPIC BLUE | IHS/SPG | SF23 UW0UW04625 1PC PRTVTG TRP BLUE EU |  | Bulk |  | TJTWI_UW0UW046250G2_EURPB_PRS | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 2000177901 | 10 | 8002660504 | 1 | 1 | 13.21 | 1.08 | 25 | 11 | 0.0906 | 2023-01-17 | 2023-01-20 | 2023-01-20 | 2023-02-02 | 2023-02-09 | 8 | 0 | 0 | 0 | 2022-12-10 | 2023-02-09 |  | Swimsuit | WOMEN | 0% |  | SOQ3-2022[Day-2] |  |  |  | SECTION 4
H403 | 7000836197 | FUW0UW046250G2 | UW0UW04625 | VINTAGE TROPIC BLUE | IHS/SPG | SF23 UW0UW04625 1PC PRTVTG TRP BLUE EU |  | Bulk |  | TJTWI_UW0UW046250G2_EURPB | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 1000915572 | 10 | 8002660505 | 359 | 359 | 13.21 | 46.67 | 25 | 376 | 0.9549 | 2023-01-17 | 2023-01-20 | 2023-01-23 | 2023-02-02 | 2023-02-09 | 7 | 0 | 0 | 0 | 2022-12-10 | 2023-02-09 |  | Swimsuit | WOMEN | 100% |  | SOQ3-2022[Day-2.09] |  |  |  | SECTION 4
H403 | 7000836198 | FUW0UW046250G2 | UW0UW04625 | VINTAGE TROPIC BLUE | IHS/SPG | SF23 UW0UW04625 1PC PRTVTG TRP BLUE EU2 |  | Bulk |  | TJTWI_UW0UW046250G2_EU2 | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 1000925183 | 10 | 8002681660 | 164 | 164 | 13.21 | 52 | 25 | 531 | 0.3086 | 2023-01-18 | 2023-01-23 | 2023-01-23 | 2023-02-02 | 2023-02-09 | 7 | 0 | 0 | 0 |  | 2023-02-09 |  | Swimsuit | WOMEN | 100% |  | SOQ3-2022[Day-3.05] |  |  |  | SECTION 4
H403 | 7000836195 | FUW0UW0462503A | UW0UW04625 | SPELL OUT JUNE IRIS | IHS/SPG | SF23 UW0UW04625 1PC PRTSPL JUNE IRIS EU |  | Bulk |  | TJTWI_UW0UW0462503A_EURPB_PRS | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 2000177900 | 10 | 8002660501 | 1 | 1 | 13.21 | 0.4 | 25 | 4 | 0.2446 | 2023-01-18 | 2023-01-23 | 2023-01-23 | 2023-02-02 | 2023-02-09 | 7 | 0 | 0 | 0 | 2023-02-09 | 2023-02-09 |  | Swimsuit | WOMEN | 100% |  | SOQ3-2022[Day-1.13] |  |  |  | SECTION 4
H403 | 7000836195 | FUW0UW0462503A | UW0UW04625 | SPELL OUT JUNE IRIS | IHS/SPG | SF23 UW0UW04625 1PC PRTSPL JUNE IRIS EU |  | Bulk |  | SUPF23 TH UW0UW0462503A TOP | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 2000179745 | 10 | 8002694959 | 4 | 4 | 13.21 | 3 | 25 | 31 | 0.1305 | 2023-01-18 | 2023-01-23 | 2023-01-24 | 2023-02-02 | 2023-02-09 | 6 | 0 | 0 | 0 | 2023-02-09 | 2023-02-09 |  | Swimsuit | WOMEN | 0% |  | INITIAL CURVE[Day-1] |  |  |  | SECTION 4
H403 | 7000836196 | FUW0UW0462503A | UW0UW04625 | SPELL OUT JUNE IRIS | IHS/SPG | SF23 UW0UW04625 1PC PRTSPL JUNE IRIS MEX |  | Bulk |  | TJTWI_UW0UW0462503A_MEX | Mexico | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100326 | CALVIN KLEIN BEACH | 1000915588 | 10 | 8002660503 | 421 | 421 | 13.21 | 28 | 25 | 275 | 1.5314 | 2023-01-19 | 2023-01-24 | 2023-01-25 | 2023-02-02 | 2023-02-09 | 5 | 0 | 0 | 0 | 2023-02-09 | 2023-02-09 |  | Swimsuit | WOMEN | 100% |  | SOQ3-2022[Day-1.13] |  |  |  | SECTION 4
H403 | 7000836195 | FUW0UW0462503A | UW0UW04625 | SPELL OUT JUNE IRIS | IHS/SPG | SF23 UW0UW04625 1PC PRTSPL JUNE IRIS EU |  | Bulk |  | TJTWI_UW0UW0462503A_EURPB | Netherlands | CHIRANAMARATHUNGA | 3SU | Calvin Klein | 100252 | CALVIN KLEIN BEACH | 1000915571 | 10 | 8002660502 | 329 | 329 | 13.21 | 36 | 25 | 455 | 0.7228 | 2023-01-20 | 2023-01-25 | 2023-01-26 | 2023-02-02 | 2023-02-09 | 4 | 0 | 0 | 0 | 2023-02-09 | 2023-02-09 |  | Swimsuit | WOMEN | 100% |  | SOQ3-2022[Day-2.66] |  |  |  | SECTION 4
H403 | 7000811740 | 172745WT0002 | 172745 | WHITE | P | JCREW_172745_BK322_SPORT BRA_WT002 | SD | Bulk |  | 1766480 | United States | Aruna Hettiarachchi | 3SU | Jcrew | 100807 | JCREW | 2000170410 | 20 | 8002660472 | 1 | 1 | 14.61 | 1.2 | 25 | 11 | 0.0902 | 2023-01-16 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-15 | 8 | 0 | 0 | 0 | 2022-11-28 | 2023-01-03 |  | Bra Non underwired | WOMEN | 0% |  | SOQ1[Day-1] |  |  |  | SECTION 4
H403 | 7000811740 | 172745WT0002 | 172745 | WHITE | P | JCREW_172745_BK322_SPORT BRA_WT002 | SD | Bulk |  | 1766480 | United States | Aruna Hettiarachchi | 3SU | Jcrew | 100807 | JCREW | 2000170410 | 10 | 8002660471 | 1 | 1 | 14.61 | 1.2 | 25 | 11 | 0.0902 | 2023-01-16 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-15 | 8 | 0 | 0 | 0 | 2022-11-28 | 2023-01-03 |  | Bra Non underwired | WOMEN | 100% |  | SOQ1[Day-1] |  |  |  | SECTION 4
H403 | 7000811740 | 172745WT0002 | 172745 | WHITE | P | JCREW_172745_BK322_SPORT BRA_WT002 | SD | Bulk |  | 1766480 | United States | Aruna Hettiarachchi | 3SU | Jcrew | 100807 | JCREW | 1000879107 | 10 | 8002660470 | 612 | 612 | 14.61 | 30 | 25 | 219 | 2.7921 | 2023-01-16 | 2023-01-26 | 2023-02-01 | 2023-02-10 | 2023-02-15 | 5 | 0 | 0 | 0 | 2023-02-15 | 2023-02-15 | QCO | Bra Non underwired | WOMEN | 100% |  | SOQ1[Day-1.09] |  |  |  | SECTION 4
H403 | 7000809536 | F4239-20-R-00PESTO-B | 4239-20 | GREEN | IHS | UN-R ONE PIEC SCOOP DOUBL KNIT-OP SD 3SP | SD | Sample-TOP |  | NEWCO SP23 MTL/TOP | United States | AmrithFrnando | 3SP | Unsubscribed | 100710 | WOMEN | 2000169110 | 170 | 8002599983 | 6 | 6 | 14.846 | 6 | 24 | 52 | 0.1145 | 2023-01-30 | 2023-02-02 | 2023-02-02 | 2022-12-05 | 2022-12-09 | -39 | 0 | 0 | 0 | 2022-11-29 | 2022-12-07 |  | Swimsuit | FL | 0% |  | SOQ3-2022[Day-1] |  |  |  | SECTION 4
H403 | 7000809536 | F4239-20-R-00PESTO-B | 4239-20 | GREEN | IHS | UN-R ONE PIEC SCOOP DOUBL KNIT-OP SD 3SP | SD | Bulk |  | 1023833-2 CTN PER SKU-E-3SP-- | United States | AmrithFrnando | 3SP | Unsubscribed | 100710 | WOMEN | 1000877597 | 20 | 8002599984 | 66 | 66 | 14.846 | 20 | 24 | 175 | 0.378 | 2023-01-30 | 2023-02-02 | 2023-02-02 | 2023-01-17 | 2023-01-20 | -11 | 0 | 0 | 0 | 2022-11-29 | 2022-12-07 |  | Swimsuit | FL | 100% |  | SOQ3-2022[Day-1.11] |  |  |  | SECTION 4
H403 | 7000819561 | F4239-20-R-GLXYBLU-B | 4239-20 | ROYAL BLUE | IHS | UN-R SCOOP DOUBLE KNIT-OP SD 3SP | SD | Sample-TOP |  |  |  |  | 3SP | Unsubscribed | 100710 | WOMEN | 2000169110 | 260 | 8002599988 | 7 | 7 | 14.846 | 6 | 24 | 52 | 0.1336 | 2023-01-30 | 2023-02-02 | 2023-02-02 | 2022-12-05 | 2022-12-09 | -39 | 0 | 0 | 0 | 2022-12-09 | 2022-12-16 |  | Swimsuit | FL | 100% |  | SOQ3-2022[Day-1.49] |  |  |  | SECTION 4
H403 | 7000819561 | F4239-20-R-GLXYBLU-B | 4239-20 | ROYAL BLUE | IHS | UN-R SCOOP DOUBLE KNIT-OP SD 3SP | SD | Bulk |  | 1023833-2 CTN PER SKU-C-SP1 | United States | AmrithFrnando | 3SP | Unsubscribed | 100710 | WOMEN | 1000901412 | 10 | 8002623182 | 127 | 127 | 14.846 | 42.4 | 24 | 224 | 0.567 | 2023-01-30 | 2023-02-02 | 2023-02-07 | 2023-01-17 | 2023-01-20 | -12 | 0 | 0 | 0 | 2023-01-06 | 2022-12-23 |  | Swimsuit | FL | 100% |  | SOQ3-2022[Day-1.63] |  |  |  | SECTION 4
H403 | 7000809535 | F4239-20-R-TRUEBLK-B | 4239-20 | BLACK | IHS | UN-R ONE PIEC SCOOP DOUBL KNIT-OP SD 3SP | SD | Sample-TOP |  | NEWCO SP23 MTL/TOP | United States | AmrithFrnando | 3SP | Unsubscribed | 100710 | WOMEN | 2000169110 | 10 | 8002599981 | 7 | 7 | 14.846 | 9 | 24 | 79 | 0.0891 | 2023-01-31 | 2023-02-07 | 2023-02-07 | 2022-12-05 | 2022-12-09 | -40 | 0 | 0 | 0 | 2022-11-14 | 2022-12-16 |  | Swimsuit | FL | 100% |  | SOQ3-2022[Day-2.19] |  |  |  | SECTION 4
H403 | 7000809535 | F4239-20-R-TRUEBLK-B | 4239-20 | BLACK | IHS | UN-R ONE PIEC SCOOP DOUBL KNIT-OP SD 3SP | SD | Bulk |  | 1023833-2 CTN PER SKU-E-3SP-- | United States | AmrithFrnando | 3SP | Unsubscribed | 100710 | WOMEN | 1000877597 | 10 | 8002599982 | 148 | 148 | 14.846 | 36 | 24 | 314 | 0.4709 | 2023-01-31 | 2023-02-07 | 2023-02-07 | 2023-01-17 | 2023-01-20 | -12 | 0 | 0 | 0 | 2022-11-29 | 2022-12-07 |  | Swimsuit | FL | 100% |  | SOQ3-2022[Day-2.28] |  |  |  | SECTION 4
7 Day(s) Gap.
H403 | 7000816019 | F1132115_CW28_ECOM | 1132115 | LBSU23177_SPLASHOMBRE_CW28 W/ MARITIME | CO/IHS/MTC/PIN/PL/P/US | 1132115 CW28 ECOM OMBRE BIKINI TOP |  | Bulk |  | 665257 | United States | Aruna Hettiarachchi | 3SU | Lane Bryant | 100387 | LANE BRYANT - WOMENS | 2000170684 | 10 | 8002711444 | 6 | 6 | 14.9 | 6 | 25 | 54 | 0.1104 | 2023-02-16 | 2023-02-17 | 2023-02-17 | 2023-02-23 | 2023-03-01 | 4 | 0 | 0 | 0 | 2023-01-19 | 2023-03-01 |  | Bra Non underwired | WOMEN | 0% | GC | SOQ3-2022[Day-1] |  |  |  | SECTION 4
H403 | 7000816087 | F1132115_CW28_SOLID | 1132115 | LBSU23177_SPLASHOMBRE_CW28 W/ MARITIME | CO/IHS/MTC/PIN/PL/P/US | 1132115 CW28 SOLID OMBRE BIKINI TOP |  | Bulk |  | 665256 | United States | Aruna Hettiarachchi | 3SU | Lane Bryant | 100387 | LANE BRYANT - WOMENS | 1000885549 | 10 | 8002711451 | 396 | 396 | 14.9 | 40 | 25 | 247 | 1.6061 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 2023-02-23 | 2023-03-01 | 3 | 0 | 0 | 0 | 2023-01-19 | 2023-03-01 |  | Bra Non underwired | WOMEN | 100% | GC | SOQ3-2022[Day-1.11] |  |  |  | SECTION 4
H403 | 7000816019 | F1132115_CW28_ECOM | 1132115 | LBSU23177_SPLASHOMBRE_CW28 W/ MARITIME | CO/IHS/MTC/PIN/PL/P/US | 1132115 CW28 ECOM OMBRE BIKINI TOP |  | Bulk |  | 665257 | United States | Aruna Hettiarachchi | 3SU | Lane Bryant | 100387 | LANE BRYANT - WOMENS | 1000885548 | 10 | 8002711443 | 602 | 602 | 14.9 | 44 | 25 | 441 | 1.3655 | 2023-02-16 | 2023-02-20 | 2023-02-22 | 2023-02-23 | 2023-03-01 | 1 | 0 | 0 | 0 | 2023-02-01 | 2023-03-01 |  | Bra Non underwired | WOMEN | 100% | GC | SOQ3-2022[Day-2.72] |  |  |  | SECTION 4
H403 | 7000821267 | F80661462GI000 | 80661 | LITTLE MERMAID BLUE | _ | 80661 462 G DISNEY LITTLE MERMAID 1 PC | PR | Bulk |  | 26159 WASH TEST AND LINE REF | United States | KANISHKASURANGA | SUM | Hanna Andersson | 100380 | GIRLS | 2000171881 | 10 | 8002642388 | 3 | 3 | 8.495 | 4 | 16 | 41 | 0.0737 | 2023-02-17 | 2023-02-22 | 2023-02-22 | 2023-01-19 | 2023-01-24 | -21 | 0 | 0 | 0 | 2023-01-04 | 2023-01-24 |  | Swimsuit | INFANT | 0% |  | SOQ3-2022[Day-1] |  |  |  | SECTION 4
H403 | 7000821267 | F80661462GI000 | 80661 | LITTLE MERMAID BLUE | _ | 80661 462 G DISNEY LITTLE MERMAID 1 PC | PR | Bulk |  | 26159 | United States | KANISHKASURANGA | SUM | Hanna Andersson | 100380 | GIRLS | 1000893758 | 10 | 8002642387 | 2066 | 2066 | 8.495 | 46 | 16 | 432 | 4.7841 | 2023-02-17 | 2023-02-22 | 2023-03-01 | 2023-01-19 | 2023-01-24 | -25 | 0 | 0 | 0 | 2023-01-04 | 2023-01-24 |  | Swimsuit | INFANT | 100% |  | SOQ3-2022[Day-1.07] |  |  |  | SECTION 4